## Risk_Register
Risk # | Date | The Risk of/That | Caused by | Resulting In | Consequence/Impact | Likelihood Score | Impact Score | Risk Score | Priority (H, M, L) | Mitigation | Risk Owner | Open/Closed
1 | 2026-03-03 | Cybersecurity breach or ransomware event disrupts RPM monitoring and exposes patient data | Expansion of IoT‑connected RPM devices, cloud-based vendor platforms, and increased endpoints (attack surface) in the RPM ecosystem | Service downtime, delayed clinical escalation, potential privacy breach, reputational damage and reduced RPM adoption | Operational disruption to monitoring workflows; legal/compliance exposure under BC/Canadian privacy requirements; recovery/remediation costs; loss of patient/provider trust and competitive disadvantage versus private digital health providers | 3 | 5 | 15 | H | Zero‑trust access controls (MFA/least privilege), encryption in transit/at rest, continuous vulnerability management & patch SLAs, device/vendor security reviews, ransomware playbook + backups and incident response drills, staff phishing training | Chief Information Security Officer (CISO) / Digital Health | Open
2 | 2026-03-03 | RPM program adoption slows as patients/providers choose competing private digital health options | Entry into a competitive, technology-driven digital health market where private firms (e.g., large telehealth providers) offer faster onboarding, integrated apps, and stronger consumer experience | Lower RPM enrollment growth, underutilized RPM capacity, weaker strategic influence in digital healthcare delivery | Strategic loss of digital health leadership; operational inefficiency (devices/staffing underused); reduced justification for expansion funding; diminished system benefits (avoidable admissions not reduced as planned) | 3 | 4 | 12 | M | Improve patient experience and onboarding time, expand clinician champions and referral pathways, targeted outreach/education, service-level targets for enrollment and response, partnership/contracting to enhance platform capabilities, monitor competitor offerings | Executive Director, Virtual Care / Digital Health Strategy | Open
3 | 2026-03-03 | Opportunity to strengthen Fraser Health’s digital health leadership through rapid scaling of RPM | Rising demand for remote monitoring and chronic care support, plus system pressure to shift care from hospital to home | Higher RPM adoption, improved outcomes, and efficiency gains—creating competitive advantage in BC’s digital health ecosystem | Operational: fewer avoidable admissions and better capacity management; financial: improved resource efficiency and stronger case for sustained funding; strategic: enhanced reputation as a digital health leader and higher stakeholder confidence | 4 | 5 | 20 | H | Scale eligibility cohorts and enrollment capacity, secure device supply/vendor SLAs, integrate RPM into care pathways/EMR, invest in analytics for early deterioration detection, track equity access (rural/underserved) and adjust deployment | Chief Medical Information Officer (CMIO) / Digital Innovation | Open