Organization: Fraser Health Authority

Scenario: Adoption of Remote Patient Monitoring (RPM)

Organization: Fraser Health Authority

Scenario: Adoption of Remote Patient Monitoring (RPM)

# Risk Identification and Risk Register Analysis

To evaluate the risks associated with the RPM initiative, we used a structured Risk Register approach. Each risk was developed using the required format: “The risk of… caused by… resulting in…”. We also evaluated each risk using likelihood and impact scoring to determine the overall risk score and priority level. Additionally, Key Risk Indicators (KRIs) were identified to support proactive monitoring of emerging risk conditions.

# Risk 1: Cybersecurity Breach Event (Negative Risk) Problem Statement Integration

Healthcare organizations are increasingly targeted by cyberattacks because patient data is highly valuable and healthcare service disruptions create pressure to resolve incidents quickly. Fraser Health’s expansion of RPM services introduces additional cybersecurity exposure due to connected medical devices, cloud-based platforms, and external vendor systems. This

competitive threat requires monitoring because a major cybersecurity incident could disrupt digital healthcare services and weaken Fraser Health’s reputation compared with private digital health providers that emphasize secure technology platforms.

# Risk Statement

The risk of cybersecurity breach or ransomware event disrupting RPM monitoring services and exposing patient data caused by the expansion of IoT-connected RPM devices, cloud-based vendor platforms, and increased digital endpoints in the RPM ecosystem resulting in service downtime, delayed clinical escalation, privacy breaches, reputational damage, and reduced RPM adoption.

# Impact Statement

If this risk occurs, Fraser Health may experience operational disruption in patient monitoring workflows, which could delay clinical interventions and negatively affect patient safety. Exposure of patient data could lead to legal and regulatory consequences under British Columbia and Canadian privacy legislation. The organization may also incur significant financial costs associated with system recovery, cybersecurity remediation, and incident response. In addition, reputational damage may reduce patient and provider trust in Fraser Health’s digital health services, creating a competitive disadvantage compared to private telehealth providers offering alternative digital healthcare platforms.

# Risk Assessment

Likelihood Score: 3

Impact Score: 5

Risk Score: 15 Priority Level: High

# Key Risk Indicator (KRI)

Number of critical cybersecurity vulnerabilities detected in Remote Patients Monitoring systems.

# Traffic Light Thresholds

Green (Optimized): 0–2 critical vulnerabilities detected

Amber (Warning): 3–5 vulnerabilities detected; mitigation actions required

Red (Critical): More than 5 vulnerabilities or confirmed security breach; immediate response required

# Mitigation Strategy

To mitigate this risk, Fraser Health should implement zero-trust security architecture including multi-factor authentication and least-privilege access controls. Patient data should be encrypted both in transit and at rest. Continuous vulnerability monitoring and patch management should be implemented for all connected devices and vendor platforms. Vendor security assessments should also be conducted regularly. In addition, ransomware response plans, system backups, incident response exercises, and staff phishing awareness training should be implemented to strengthen cybersecurity resilience.

# Risk Owner

Chief Information Security Officer (CISO) / Digital Health

# Risk 2: Competitive Pressure from Private Digital Health Providers (Negative Risk) Problem Statement Integration

Fraser Health’s adoption of RPM services places the organization within a rapidly evolving digital healthcare market. Private telehealth providers and digital health companies offer advanced platforms that include integrated mobile applications, faster patient onboarding, and enhanced consumer experience. This competitive pressure must be monitored because private providers may attract patients who prefer more convenient or technologically advanced healthcare services.

# Risk Statement

The risk of RPM program adoption slowing as patients and healthcare providers choose competing private digital health services caused by Fraser Health’s entry into a competitive

digital healthcare market where private firms offer faster onboarding, integrated digital applications, and stronger consumer experience resulting in lower RPM enrollment growth, underutilized monitoring capacity, and weaker strategic influence in digital healthcare delivery.

# Impact Statement

If Fraser Health’s RPM services fail to remain competitive, enrollment growth may decline, resulting in underutilized RPM infrastructure and healthcare resources. Lower adoption may reduce the program’s effectiveness in improving chronic disease management and reducing hospital admissions. Operational inefficiencies may arise if staffing, devices, and monitoring systems are not fully utilized. Strategically, Fraser Health may lose its position as a leader in digital healthcare innovation and face difficulty securing future funding for digital health expansion.

# Risk Assessment

Likelihood Score: 3

Impact Score: 4

Risk Score: 12

Priority Level: Medium

# Key Risk Indicator (KRI)

Quarterly RPM enrollment growth rate.

# Traffic Light Thresholds

Green (Optimized): Enrollment growth above 8%

Amber (Warning): Enrollment growth between 3% and 8%

Red (Critical): Enrollment growth below 3%

# Mitigation Strategy

To address this risk, Fraser Health should improve the digital user experience and streamline RPM onboarding processes. Clinician engagement should be strengthened by developing clinical champions and improving referral pathways. Targeted patient outreach and education programs should also be implemented to increase awareness of RPM services. Service-level targets should

be established for enrollment and response times. Partnerships with technology vendors may also enhance platform capabilities and ensure Fraser Health remains competitive in the digital healthcare market.

# Risk Owner

Executive Director, Virtual Care / Digital Health Strategy

# Risk 3: Opportunity to Strengthen Digital Health Leadership (Positive Risk) Problem Statement Integration

Demand for remote healthcare services continues to increase as healthcare systems seek more efficient models of care delivery. Remote Patient Monitoring enables healthcare providers to monitor patients outside hospital settings, reducing unnecessary hospital visits and improving chronic disease management. This opportunity requires monitoring because successful expansion of RPM services could strengthen Fraser Health’s leadership position in digital healthcare and improve system performance.

# Risk Statement

The opportunity to strengthen Fraser Health’s digital health leadership through rapid scaling of RPM services caused by rising demand for remote monitoring and increasing system pressure to shift healthcare delivery from hospitals to home resulting in higher RPM adoption, improved patient outcomes, and greater healthcare system efficiency.

# Impact Statement

If Fraser Health successfully expands RPM services, patient outcomes may improve through earlier detection of clinical deterioration and faster intervention. Healthcare system efficiency may increase through fewer avoidable hospital admissions and improved capacity management. Financial benefits may also occur through more efficient use of healthcare resources and stronger justification for continued digital health funding. Strategically, Fraser Health may enhance its reputation as a leader in digital healthcare innovation and strengthen stakeholder confidence in its digital transformation initiatives.

# Risk Assessment

Likelihood Score: 4

Impact Score: 5

Risk Score: 20 Priority Level: High

# Key Risk Indicator (KRI)

Percentage of eligible patients enrolled in RPM programs.

# Traffic Light Thresholds

Green (Optimized): Enrollment above 60%

Amber (Warning): Enrollment between 40% and 60%

Red (Critical): Enrollment below 40%

# Opportunity Strategy

To leverage this opportunity, Fraser Health should expand RPM eligibility criteria and increase enrollment capacity. Vendor agreements should be established to ensure sufficient device supply and platform scalability. RPM services should be integrated into existing care pathways and electronic medical record systems to improve clinician adoption. Investment in data analytics can support early detection of patient deterioration and improve decision-making. Monitoring access equity will also ensure that rural and underserved communities benefit from RPM services.

# Reference

Cyber Security Centre of Canada. (2024). National cyber threat assessment 2025–2026. Government of Canada. https://www.cyber.gc.ca/en/guidance/national-cyber-threat- assessment-2025-2026

Fraser Health Authority. (2024). Remote patient monitoring services. Fraser Health. https://www.fraserhealth.ca/patients-and-visitors/virtual-health/remote-patient-monitoring

Government of British Columbia. (2023). BC digital health strategy. Ministry of Health. https://www2.gov.bc.ca/assets/gov/health/about-bc-s-health-care-system/